Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" / "Finished in Sprint 3" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product Backlog
Product Name:	C1325 Library Management System					Complete Fields in Green!!!
Team ID:

Name:	George F. Rice
Initials:	GFR
Student ID:

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	8		Total
Sprint 1 Left	0	8	1
Sprint 2 Left	0	0	2
Sprint 3 Left	0	0	3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
			Sprints
Feature ID	Priority		Planned	Status	As a...	I want to...	So that...	Notes
AP	1		1	Finished in Sprint 1	Librarian	Add a publication	I can keep track of what is in the library
LP	2		1	Finished in Sprint 1	Librarian	List all publications	I can find out what is in the library	This will also be needed for the next two features
CO	3		1	Finished in Sprint 1	Librarian	Check out a publication	I can track who has borrowed each publication	Each publication will need to know if it is checked out or not
CI	4		1	Finished in Sprint 1	Librarian	Check in a publication	I can tell when a publication is returned
HE	5		1	Finished in Sprint 1	Librarian	Get help	I can learn how to use the system
PA	6		1	Finished in Sprint 1	Librarian	Add a patron	I can conveniently keep track of all patrons	This is the Bonus level
SP	7		1	Finished in Sprint 1	Librarian	Select a patron when checking out a pub	I don't have to rekey recurring patron info	This is the Bonus level
CU	8		1	Finished in Sprint 1	Librarian	Add custom info for each publication type	I can keep better track of library assets	This is the Extreme Bonus level
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Feb 22		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Mar 01
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	28
Day 1 Left	21	7
Day 2 Left	15	6
Day 3 Left	9	6
Day 4 Left	8	1
Day 5 Left	1	7
Day 6 Left	1	0
Day 7 Left	0	1

	Feature ID		Description	Status	Notes
	AP		Implement enums.h for age, genre, and media	Completed Day 1	Includes a test with each constructor and method
	AP		Create a Publication class with data and a constructor	Completed Day 1
	AP		Add the to_string method to Publication	Completed Day 1	Useful for testing the class
	AP		Add the is_checked_out method to Publication	Completed Day 1
	AP		Add the check_out method to Publication	Completed Day 1
	AP		Add the check_in method to Publication	Completed Day 1
	AP		Implement Publication regression test	Completed Day 1
	AP		Implement Invalid_transaction exception	Completed Day 2
	AP		Add the check_in method to Publication	Completed Day 2
	AP		Implement Library class with vector of publications	Completed Day 2
	AP		Implement Library::add_publication	Completed Day 2
	AP		Implement main menu	Completed Day 2
	AP		Implement main menu (1) Add publication	Completed Day 2
	LP		Implement Library::number_of_publications	Completed Day 3
	LP		Implement main menu (2) List all publications	Completed Day 3
	CO		Implement Library::check_out	Completed Day 3
	CO		Implement main menu (3) Check out publication	Completed Day 3
	CI		Implement Library::check_in	Completed Day 3
	CI		Implement main menu (4) Check in publication	Completed Day 3
	HE		Implement main menu (9) Help	Completed Day 4
	PA		Implement Patron class with constructor and getters	Completed Day 5
	PA		Implement Patron::to_string	Completed Day 5
	PA		Implement Patron class regression tests	Completed Day 5
	PA		Implement main menu (5) Add patron	Completed Day 5
	PA		Implement main menu (6) List patrons	Completed Day 5
	SP		Change from entering patron data to selecting patron on checkout	Completed Day 5
	SP		Update help file to cover management of patrons	Completed Day 5
	CU		Add and manage derived classes	Completed Day 7
Sprint Burn Chart
Tasks
Days